## Sheet1
Time (h) | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20 | 20.5 | 21 | 21.5 | 22 | 22.5 | 23 | 23.5 | 24 | 24.5 | 25 | 25.5 | 26 | 26.5 | 27 | 27.5 | 28 | 28.5 | 29 | 29.5 | 30
Task Name
Systems Analysis and Initial Presentation (TIME GUESSED)
1. Initial Planning
2. Create Use Case Diagrams |  |  | :1
3. Create Sequence Diagrams |  |  |  |  | :2
4. Create Context Diagram |  |  |  |  | :2
5. Create Data Flow Diagrams | [7 empty] | :4
6. Assemble SA Presentation | [10 empty] | :5
7. Present | [15 empty] | :6
Third Party Component Investigation (TIME GUESSED)
8. Research Third Party Component | [16 empty] | :7
9. Install Third Party Component | [17 empty] | :8
Prototype Construction (TIME GUESSED)
10. Understand How To Use Component for Communication | [27 empty] | :9
11. Create Minimal Prototype Server | [31 empty] | :10
12. Create Minimal Prototype Client | [31 empty] | :10
13. Test Prototype | [34 empty] | :11,12
Working Client Construction
14. Implement Client-Server Communication | [35 empty] | :13
15. Implement Inter-Process Communication (IPC) | [35 empty] | :13
16. Implement Main Routine | [38 empty] | :14,15
17. Home Testing | [39 empty] | :16
Working Server Construction
18. Implement Server Model | [35 empty] | :13
19. Implement Server View | [41 empty] | :21
20. Implement Server Controller (Interface) | [35 empty] | :13
21. Implement QT GUI Interface | [35 empty] | :13
22. Implement Main Routine | [43 empty] | :18,19,20,21
23. Home Testing | [45 empty] | :22
External Testing
24. Test Client and Server on Third-Party Computers | [47 empty] | :17,23
Game Integration
25. Diffusion of client to game team members | [50 empty] | :24
26. Test if teams can connect and communicate with server | [52 empty] | :25
27. Play Games! | [53 empty] | :26
Overhead
X. Overhead (all)
| Legend: | [33 empty] | Past << | >> Future
|  | Completed | [32 empty] | 1750 | 1250
Future